## Promotional Timeline Calculator
Event Date AMEND | 2023-12-20
Start Promoting (8 weeks prior) | 2023-10-25
Promotion channel | Submission deadline | Deadline Date to inform departments of requirements | Weeks prior to live event
UoR Homepage | One month's notice | 2023-09-27 | 12 weeks prior
MERL social | One month's notice | 2023-09-27 | 12 weeks prior
Ordering printed and promotional material (banners, lollipops, flags etc.) | 4 weeks notice | 2023-09-27 | 12 weeks prior
Events Listings | Two week's notice (but the more time, the more advertising) | 2023-10-11 | 10 weeks prior
Essentials (Student website) | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Me@Reading Student | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Carrington and Palmer screen | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Student Instagram | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Student Twitter | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Student YouTube | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Student Events | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Student blog | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
UoR Student App | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
Community newsletter | Termly - contact Molli to confirm when next one is going out | 2023-10-11 | 10 weeks prior
Connected (fortnightly online alumni magazine) | Minimum two weeks notice | 2023-10-11 | 10 weeks prior
Alumni email invite | Minimum two weeks notice | 2023-10-11 | 10 weeks prior
Alumni website | Minimum two weeks notice | 2023-10-11 | 10 weeks prior
SU digital marketing | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
SU socials (main site) | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
SU Venue socials | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
SU Activities & Opportunities socials | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
SU PR/Officer related Comms | Minimum 2 weeks | 2023-10-11 | 10 weeks prior
What's On e-newsletter | Ad hoc posting of e-newsletter so if interested, contact us for our next date | 2023-10-18 | 9 weeks prior
Social Media | End of week 3 of the month for events round-up. | 2023-10-18 | 9 weeks prior
Staff Portal (headline) | One week notice | 2023-10-18 | 9 weeks prior
InBrief e-newsletter | One week notice | 2023-10-18 | 9 weeks prior
Henley Live | One week notice | 2023-10-18 | 9 weeks prior
Buzz (Henley intranet) | One week notice | 2023-10-18 | 9 weeks prior
Watercooler (Henley internal email) | Fortnightly | 2023-10-18 | 9 weeks prior
Social Media | General ad-hoc with as much notice as possible. | 2023-10-25 | 8 weeks prior
Community Action Partnership Team Channel | Self-upload when required | 2023-10-25 | 8 weeks prior
Alumni social | Ad/hoc as needed | 2023-10-25 | 8 weeks prior
Newsletter, blog, website, events listings | Contact for newsletter deadlines | 2023-10-25 | 8 weeks prior
Research emails | Send email directly to the email address you require at anytime. | 2023-10-25 | 8 weeks prior